## Product-Backlog
PRODUCT BACKLOG ROLE BASED EMPLOYEE MANAGEMENT SYSTEM MODULE
PRODUCT BACKLOG REPORT
ID | MODULE | AS A … | I WANT TO … | SO THAT … | PRIORITY | STORY POINTS | SPRINT | STATUS | STATUS | PRIORITY
PB-01 | Authentication & Access | New User | Register into the system | I can create my account and access the portal | High | 5 | 1 | To-Do | To-Do | High
PB-02 | Authentication & Access | Registered User | Login using my credentials | I can securely access my dashboard | High | 5 | 1 | To-Do | In-Progress | Medium
PB-03 | Authentication & Access | Admin | Assign roles to users | Users can access features based on their responsibilities | High | 3 | 1 | To-Do | Complete | Low
PB-04 | Authentication & Access | User | Be redirected to role-based dashboard after login | I see features relevant to my role | High | 5 | 2 | To-Do | Overdue
PB-05 | Authentication & Access | User | Change my password | I can maintain account security | Medium | 3 | 2 | To-Do | On Hold
PB-06 | Authentication & Access | User | Reset my password if forgotten | I can regain access to my account | Medium | 5 | 2 | To-Do
PB-07 | Authentication & Access | System Admin | Restrict unauthorized access | Only authenticated users can use the system | High | 5 | 2 | To-Do
PB-08 | Employee Management | Admin | Add a new employee | I can onboard new staff into the organization | High | 5 | 3 | To-Do
PB-09 | Employee Management | Admin | Update employee details | I can keep employee information accurate and up to date | High | 3 | 3 | To-Do
PB-10 | Employee Management | Admin | Delete employee records | I can remove inactive or resigned employees from the system | Medium | 3 | 3 | To-Do
PB-11 | Employee Management | Admin | View the list of all employees | I can monitor and manage workforce information | High | 5 | 3 | To-Do
PB-12 | Employee Management | Admin | Search employees by name or department | I can quickly find specific employee records | High | 5 | 4 | To-Do
PB-13 | Employee Management | Admin | View employees with pagination | I can manage large employee data efficiently | Medium | 3 | 4 | To-Do
PB-14 | Department Management | Admin | Create new departments | I can organize employees under structured units | High | 5 | 4 | To-Do
PB-15 | Department Management | Admin | Assign employees to departments | Employees are mapped correctly to their respective teams | High | 5 | 4 | To-Do
PB-16 | Leave Management | Employee | Apply for leave | I can request time off from work officially | High | 5 | 5 | To-Do
PB-17 | Leave Management | Employee | View my leave history | I can track my previous leave applications | Medium | 3 | 5 | To-Do
PB-18 | Leave Management | Employee | Track the status of my leave request | I know whether it is pending, approved, or rejected | High | 3 | 5 | To-Do
PB-19 | Leave Management | Manager | Approve leave requests | I can authorize employee leave based on company policy | High | 5 | 6 | To-Do
PB-20 | Leave Management | Manager | Reject leave requests | I can decline leave if it does not meet requirements | Medium | 3 | 6 | To-Do
PB-21 | Leave Management | Admin | Maintain leave balance for employees | Leave availability is accurately tracked | High | 5 | 6 | To-Do
PB-22 | Leave Management | Admin | View overall leave summary | I can monitor leave trends across the organization | Medium | 3 | 6 | To-Do
PB-23 | Dashboard & Reporting | Admin | View total number of employees | I can monitor overall workforce size | Medium | 3 | 7 | To-Do
PB-24 | Dashboard & Reporting | Admin | View department-wise employee distribution | I can analyze organizational structure | Medium | 5 | 7 | To-Do
PB-25 | Dashboard & Reporting | Manager | View pending leave requests count | I can take timely action on approvals | High | 3 | 7 | To-Do
PB-26 | Dashboard & Reporting | Admin | View graphical charts for employee and leave data | I can understand system insights visually | Medium | 5 | 7 | To-Do
PB-27 | Profile Management | User | View my profile details | I can see my personal and employment information | Medium | 3 | 8 | To-Do
PB-28 | Profile Management | User | Update my profile information | I can keep my personal details accurate | Medium | 3 | 8 | To-Do
PB-29 | Profile Management | User | Upload or change my profile picture | My profile remains updated and identifiable | Low | 3 | 8 | To-Do
PB-30 | System Enhancement | Admin | Validate all forms with proper error messages | The system maintains data accuracy and usability | Medium | 5 | 8 | To-Do
TOTAL | [5 empty] | 122

## Sprint-Backlog
AGILE SPRINT BACKLOG ROLE BASED EMPLOYEE MANAGEMENT SYSTEM MODULE WITH BURNDOWN CHART
SPRINT NO. | BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
1 | User Story #1- User Registration | 5 |  | To-Do
1 | Design registration form layout |  | Akshat Sharma | To-Do | 4 | 4 | 0 | 0 | 0 | 0
1 | Implement registration backend logic |  | Akshat Sharma | To-Do | 4 | 2 | 2 | 0 | 0 | 0
1 | Add validation rules and connect database |  | Akshat Sharma | To-Do | 4 | 0 | 2 | 2 | 0 | 0
1 | User Story #2 - User Login | 5 |  | To-Do
1 | Design login interface |  | Akshat Sharma | To-Do | 4 | 0 | 2 | 2 | 0 | 0
1 | Implement login authentication logic |  | Akshat Sharma | To-Do | 6 | 0 | 0 | 2 | 2 | 2
1 | User Story #3 - Role Assignment | 3 |  | To-Do
1 | Implement role mapping & authorization |  | Akshat Sharma | To-Do | 4 | 0 | 0 | 0 | 2 | 2
1 | Integration testing for authentication module |  | Akshat Sharma | To-Do | 4 | 0 | 0 | 0 | 2 | 2
2 | User Story #4 - Role-based Dashboard Redirect | 5 |  | To-Do
2 | Implement role-based routing logic |  | Akshat Sharma | To-Do | 4 | 4 | 0 | 0 | 0 | 0
2 | Develop dashboard UI per role |  | Akshat Sharma | To-Do | 4 | 2 | 2 | 0 | 0 | 0
2 | Integration testing – dashboard access |  | Akshat Sharma | To-Do | 2 | 0 | 2 | 0 | 0 | 0
2 | User Story #5 - Change Password | 3 |  | To-Do
2 | Create change password UI |  | Akshat Sharma | To-Do | 3 | 0 | 2 | 1 | 0 | 0
2 | Implement password update logic |  | Akshat Sharma | To-Do | 3 | 0 | 0 | 3 | 0 | 0
2 | Unit testing – change password |  | Akshat Sharma | To-Do | 2 | 0 | 0 | 0 | 2 | 0
2 | User Story #6 - Reset Password | 5 |  | To-Do
2 | Implement forgot password workflow |  | Akshat Sharma | To-Do | 4 | 0 | 0 | 2 | 2 | 0
2 | Email token generation & validation |  | Akshat Sharma | To-Do | 4 | 0 | 0 | 0 | 2 | 2
2 | User Story #7 - Restrict Unauthorized Access | 5 |  | To-Do
2 | Implement middleware for authorization |  | Akshat Sharma | To-Do | 2 | 0 | 0 | 0 | 0 | 2
2 | Integration testing – access control |  | Akshat Sharma | To-Do | 2 | 0 | 0 | 0 | 0 | 2
3 | User Story #8 - Add New Employee | 5 |  | To-Do
3 | Design Add Employee UI |  | Akshat Sharma | To-Do | 4 | 4 | 0 | 0 | 0 | 0
3 | Develop Add Employee API |  | Akshat Sharma | To-Do | 4 | 2 | 2 | 0 | 0 | 0
3 | Validation & DB integration |  | Akshat Sharma | To-Do | 2 | 0 | 2 | 0 | 0 | 0
3 | User Story #9 - Update Employee | 3 |  | To-Do
3 | Create Update Employee UI |  | Akshat Sharma | To-Do | 3 | 0 | 2 | 1 | 0 | 0
3 | Implement update API logic |  | Akshat Sharma | To-Do | 3 | 0 | 0 | 3 | 0 | 0
3 | Unit testing – update employee |  | Akshat Sharma | To-Do | 2 | 0 | 0 | 0 | 2 | 0
3 | User Story #10 - Delete Employee | 3 |  | To-Do
3 | Implement delete API logic |  | Akshat Sharma | To-Do | 3 | 0 | 0 | 2 | 1 | 0
3 | Add confirmation & validation checks |  | Akshat Sharma | To-Do | 2 | 0 | 0 | 0 | 2 | 0
3 | Unit testing – delete employee |  | Akshat Sharma | To-Do | 1 | 0 | 0 | 0 | 1 | 0
3 | User Story #11 - View All Employees | 5 |  | To-Do
3 | Develop employee listing UI |  | Akshat Sharma | To-Do | 3 | 0 | 0 | 0 | 0 | 3
3 | Implement API for employee list |  | Akshat Sharma | To-Do | 2 | 0 | 0 | 0 | 0 | 2
3 | Integration testing – employee module |  | Akshat Sharma | To-Do | 1 | 0 | 0 | 0 | 0 | 1
4 | User Story #12 - Search Employees | 5 |  | To-Do
4 | Implement search UI |  | Akshat Sharma | To-Do | 4 | 4 | 0 | 0 | 0 | 0
4 | Develop search API with filters |  | Akshat Sharma | To-Do | 4 | 2 | 2 | 0 | 0 | 0
4 | Unit testing – search functionality |  | Akshat Sharma | To-Do | 2 | 0 | 2 | 0 | 0 | 0
4 | User Story #13 -Employee Pagination | 3 |  | To-Do
4 | Implement pagination logic in API |  | Akshat Sharma | To-Do | 3 | 0 | 2 | 1 | 0 | 0
4 | Integrate pagination in UI |  | Akshat Sharma | To-Do | 3 | 0 | 0 | 3 | 0 | 0
4 | Testing – pagination accuracy |  | Akshat Sharma | To-Do | 2 | 0 | 0 | 0 | 2 | 0
4 | User Story #14 - Create Departments | 5 |  | To-Do
4 | Design department creation UI |  | Akshat Sharma | To-Do | 3 | 0 | 0 | 2 | 1 | 0
4 | Develop department API & DB schema |  | Akshat Sharma | To-Do | 3 | 0 | 0 | 0 | 3 | 0
4 | Unit testing – department module |  | Akshat Sharma | To-Do | 2 | 0 | 0 | 0 | 0 | 2
4 | User Story #15 - Assign Employees to Department | 5 |  | To-Do
4 | Implement employee-department mapping logic |  | Akshat Sharma | To-Do | 2 | 0 | 0 | 0 | 0 | 2
4 | Integration testing – department assignment |  | Akshat Sharma | To-Do | 2 | 0 | 0 | 0 | 0 | 2
5 | User Story #16- Apply for Leave | 5 |  | To-Do
5 | Design leave application UI |  | Akshat Sharma | To-Do | 4 | 4 | 0 | 0 | 0 | 0
5 | Develop leave submission API |  | Akshat Sharma | To-Do | 4 | 2 | 2 | 0 | 0 | 0
5 | Validation (date rules, balance check) |  | Akshat Sharma | To-Do | 4 | 0 | 2 | 2 | 0 | 0
5 | Unit testing – leave submission |  | Akshat Sharma | To-Do | 2 | 0 | 0 | 2 | 0 | 0
5 | User Story #17 - View Leave History | 3 |  | To-Do
5 | Develop leave history UI |  | Akshat Sharma | To-Do | 4 | 0 | 2 | 2 | 0 | 0
5 | Implement history API with filters |  | Akshat Sharma | To-Do | 4 | 0 | 0 | 2 | 2 | 0
5 | Unit testing – leave history |  | Akshat Sharma | To-Do | 2 | 0 | 0 | 0 | 2 | 0
5 | User Story #18 - Track Leave Status | 3 |  | To-Do
5 | Implement status tracking logic |  | Akshat Sharma | To-Do | 3 | 0 | 0 | 0 | 0 | 3
5 | Integration testing – leave module |  | Akshat Sharma | To-Do | 3 | 0 | 0 | 0 | 0 | 3
6 | User Story #19 - Approve Leave | 5 |  | To-Do
6 | Develop approve leave API |  | Akshat Sharma | To-Do | 4 | 4 | 0 | 0 | 0 | 0
6 | Update leave status workflow logic |  | Akshat Sharma | To-Do | 4 | 2 | 2 | 0 | 0 | 0
6 | Unit testing – approve leave |  | Akshat Sharma | To-Do | 2 | 0 | 2 | 0 | 0 | 0
6 | User Story #20 - Reject Leave | 3 |  | To-Do
6 | Implement reject leave API logic |  | Akshat Sharma | To-Do | 3 | 0 | 2 | 1 | 0 | 0
6 | Add remarks & notification handling |  | Akshat Sharma | To-Do | 3 | 0 | 0 | 3 | 0 | 0
6 | Unit testing – reject leave |  | Akshat Sharma | To-Do | 2 | 0 | 0 | 0 | 2 | 0
6 | User Story #21 - Maintain Leave Balance | 5 |  | To-Do
6 | Design leave balance logic (auto deduction) |  | Akshat Sharma | To-Do | 4 | 0 | 0 | 2 | 2 | 0
6 | Update balance after approval |  | Akshat Sharma | To-Do | 4 | 0 | 0 | 0 | 2 | 2
6 | User Story #22 - View Leave Summary | 3 |  | To-Do
6 | Develop leave summary UI |  | Akshat Sharma | To-Do | 2 | 0 | 0 | 0 | 0 | 2
6 | Integration testing – leave approval module |  | Akshat Sharma | To-Do | 2 | 0 | 0 | 0 | 0 | 2
7 | User Story #23 - Total Employees Count | 3 |  | To-Do
7 | Develop API for total employee count |  | Akshat Sharma | To-Do | 3 | 3 | 0 | 0 | 0 | 0
7 | Integrate count display in dashboard UI |  | Akshat Sharma | To-Do | 3 | 3 | 0 | 0 | 0 | 0
7 | User Story #24 - Department Distribution | 5 |  | To-Do
7 | Develop API for department-wise count |  | Akshat Sharma | To-Do | 4 | 0 | 4 | 0 | 0 | 0
7 | Integrate department data in UI |  | Akshat Sharma | To-Do | 2 | 0 | 2 | 0 | 0 | 0
7 | User Story #25 - Pending Leave Count | 3 |  | To-Do
7 | Develop API for pending leave count |  | Akshat Sharma | To-Do | 3 | 0 | 0 | 3 | 0 | 0
7 | Display pending leave count in dashboard |  | Akshat Sharma | To-Do | 3 | 0 | 0 | 3 | 0 | 0
7 | User Story #26 - Graphical Charts | 5 |  | To-Do
7 | Integrate chart library (e.g., Chart.js) |  | Akshat Sharma | To-Do | 4 | 0 | 0 | 0 | 4 | 0
7 | Bind dashboard data to charts |  | Akshat Sharma | To-Do | 4 | 0 | 0 | 0 | 2 | 2
7 | Testing – dashboard analytics module |  | Akshat Sharma | To-Do | 4 | 0 | 0 | 0 | 0 | 4
8 | User Story #27 - View Profile | 3 |  | To-Do
8 | Develop profile view API |  | Akshat Sharma | To-Do | 3 | 3 | 0 | 0 | 0 | 0
8 | Design profile display UI |  | Akshat Sharma | To-Do | 3 | 3 | 0 | 0 | 0 | 0
8 | User Story #28 - Update Profile | 3 |  | To-Do
8 | Implement update profile UI |  | Akshat Sharma | To-Do | 4 | 0 | 4 | 0 | 0 | 0
8 | Develop update profile API |  | Akshat Sharma | To-Do | 4 | 0 | 2 | 2 | 0 | 0
8 | User Story #29 - Upload Profile Picture | 3 |  | To-Do
8 | Implement file upload backend logic |  | Akshat Sharma | To-Do | 4 | 0 | 0 | 2 | 2 | 0
8 | Integrate image preview in UI |  | Akshat Sharma | To-Do | 4 | 0 | 0 | 2 | 2 | 0
8 | User Story #30 - Form Validation | 5 |  | To-Do
8 | Implement frontend validation rules |  | Akshat Sharma | To-Do | 3 | 0 | 0 | 0 | 2 | 1
8 | Backend validation & security checks |  | Akshat Sharma | To-Do | 3 | 0 | 0 | 0 | 0 | 3
| TOTAL | 122 |  |  | 238 | 48 | 48 | 50 | 46 | 46

## User story
S.NO | User Story | Acceptance Criteria
1 | As a new user, I want to register into the system so that I can create my account and access the portal. | User must enter valid name, email and password Email must be unique in the system Role should be assigned during registration Successful registration message must be displayed
2 | As a registered user, I want to login using my credentials so that I can securely access my dashboard. | User must enter valid email and password System must validate credentials Dashboard must load after successful login Error message must display for invalid login
3 | As an admin, I want to assign roles to users so that users can access features based on their responsibilities. | Admin can select role (Admin/Manager/Employee) Role must be stored in database User permissions must change based on assigned role Role update confirmation message must display
4 | As a user, I want to be redirected to role-based dashboard after login so that I see features relevant to my role. | Admin dashboard visible only to Admin Manager dashboard visible only to Manager Employee dashboard visible only to Employee Unauthorized access must be restricted
5 | As a user, I want to change my password so that I can maintain account security. | User must enter current password New password must follow validation rules Password must update successfully Confirmation message must be displayed
6 | As a user, I want to reset my password if forgotten so that I can regain access to my account. | User must provide registered email System must verify email exists Password reset option must be available User must receive confirmation after reset
7 | As a system admin, I want to restrict unauthorized access so that only authenticated users can use the system. | Only logged-in users can access system pages Unauthorized users must be redirected to login page Role-based authorization must be enforced Access violations must show proper error message
8 | As an admin, I want to add a new employee so that I can onboard new staff into the organization. | Admin must fill all required employee details Employee record must be saved in database System must validate mandatory fields Success message must be displayed
9 | As an admin, I want to update employee details so that I can keep employee information accurate and up to date. | Admin must be able to edit employee details Updated data must reflect in employee list System must validate updated fields Confirmation message must be shown
10 | As an admin, I want to delete employee records so that I can remove inactive or resigned employees from the system. | Admin must confirm before deletion Deleted employee must not appear in employee list System must prevent accidental deletion Deletion confirmation message must display
11 | As an admin, I want to view the list of all employees so that I can monitor and manage workforce information. | System must display all employee records Employee list must show basic details (Name, Role, Department) Data must load correctly from database List should be visible only to authorized users
12 | As an admin, I want to search employees by name or department so that I can quickly find specific employee records. | Search field must accept employee name or department System must display matching results If no match found, appropriate message must display Search results must refresh dynamically
13 | As an admin, I want to view employees with pagination so that I can manage large employee data efficiently. | Employee list must be divided into pages Navigation buttons (Next/Previous) must work properly Page size must limit number of records displayed Pagination must load data correctly
14 | As an admin, I want to create new departments so that I can organize employees under structured units. | Admin must enter department name Department must be saved in database Duplicate department names must be prevented Confirmation message must be shown
15 | As an admin, I want to assign employees to departments so that employees are mapped correctly to their respective teams. | Admin must select employee and department System must update employee department mapping Changes must reflect in employee list Success message must be displayed
16 | As an employee, I want to apply for leave so that I can request time off from work officially. | Employee must select leave start and end date Employee must enter reason for leave System must validate leave dates Leave request must be saved with status as "Pending"
17 | As an employee, I want to view my leave history so that I can track my previous leave applications. | System must display all previous leave requests Leave status must be visible (Pending/Approved/Rejected) Leave dates and reason must be shown Data must load correctly from database
18 | As an employee, I want to track the status of my leave request so that I know whether it is pending, approved, or rejected. | Leave status must update automatically after manager action Status must be clearly displayed Employee must not edit leave after approval/rejection Notification message must appear when status changes
19 | As a manager, I want to approve leave requests so that I can authorize employee leave based on company policy. | Manager must view pending leave requests Manager must be able to approve leave Leave status must change to "Approved" Leave balance must update automatically
20 | As a manager, I want to reject leave requests so that I can decline leave if it does not meet requirements. | Manager must be able to reject leave request Manager may provide rejection reason Leave status must change to "Rejected" Employee must be notified about rejection
21 | As an admin, I want to maintain leave balance for employees so that leave availability is accurately tracked. | System must store leave balance for each employee Leave balance must reduce after leave approval Leave balance must not go below zero Admin must be able to view leave balance details
22 | As an admin, I want to view overall leave summary so that I can monitor leave trends across the organization. | System must display total approved leaves System must display total rejected leaves Leave data must be department-wise filterable Summary must update dynamically
23 | As an admin, I want to view total number of employees so that I can monitor overall workforce size. | System must display total employee count Count must update when new employee is added or deleted Data must load correctly from database Only authorized users can view the data
24 | As an admin, I want to view department-wise employee distribution so that I can analyze organizational structure. | System must display number of employees per department Data must be accurate and updated Department data must be displayed clearly Only authorized roles can access this feature
25 | As a manager, I want to view pending leave requests count so that I can take timely action on approvals. | System must show number of pending leave requests Count must update after approval or rejection Only manager role can access this information Data must reflect real-time status
26 | As an admin, I want to view graphical charts for employee and leave data so that I can understand system insights visually. | Dashboard must display graphical representation Charts must load correct data Data must match database records Charts must be visible only to authorized users
27 | As a user, I want to view my profile details so that I can see my personal and employment information. | Profile must display name, email, role, and department Data must be retrieved from database Only logged-in user can view own profile Profile data must be accurate
28 | As a user, I want to update my profile information so that I can keep my personal details accurate. | User must be able to edit allowed fields Updated data must be saved in database System must validate updated information Confirmation message must be displayed
29 | As a user, I want to upload or change my profile picture so that my profile remains updated and identifiable. | User must be able to upload image file System must validate file type Uploaded image must be saved properly Updated picture must display in profile
30 | As an admin, I want the system to validate all forms with proper error messages so that the system maintains data accuracy and usability. | All mandatory fields must be validated Proper error messages must display for invalid input Forms must prevent submission with incomplete data Validation must work across all modules